Project Preparation

Project Name and Scope

Smart Core - Beitak Smart Odoo ERP Implementation

| Client | Beitak Smart |
| --- | --- |
| Implementation partner | Khomasi ERP |
| Project | Smart Core - Beitak Smart Odoo ERP Implementation (BTK-ERP-01) |
| Document ID | BTK-PRE-02 |
| Version | 1.0 |
| Date | 15 Oct 2026 |
| Status | Approved |
| Prepared by | Ahmed Fahmy (Project Manager) |
| Approved by | Hany Mostafa - General Manager (Beitak Smart) |

# Document Control

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0 | 15 Oct 2026 | Ahmed Fahmy | Initial release |

| Distribution | Role |
| --- | --- |
| Hany Mostafa | Project Sponsor - Beitak Smart |
| Omar Hassan | Client Project Manager |
| Khomasi ERP project team | Implementation partner |

# 1. Project Identity

| Project name | Smart Core - Beitak Smart Odoo ERP Implementation |
| --- | --- |
| Project code | BTK-ERP-01 |
| Client | Beitak Smart |
| Implementation partner | Khomasi ERP |
| Platform | Odoo 19 Enterprise (Odoo Online / Odoo.sh) |
| Project sponsor | Hany Mostafa - General Manager |
| Client project manager | Omar Hassan - IT & ERP Administrator |
| Partner project manager | Ahmed Fahmy |
| Planned go-live | 01 Jan 2027 (start of fiscal year) |
| Users / employees | 30 users / 36 employees |

The name Smart Core reflects the goal: one core system for every Beitak Smart department.

# 2. Background and Objectives

Beitak Smart runs on a legacy accounting package, Excel and a standalone cashier program. Data is re-keyed, costs are incomplete and management has no profitability by branch or business line. The project replaces these tools with Odoo.

| Objective | KPI | Baseline | Target |
| --- | --- | --- | --- |
| Accurate product cost and margin | Import shipments with landed costs allocated | 0% | 100% |
| Fewer stock-outs | Stock-out rate on top-20 SKUs | about 12% | below 3% |
| Reliable stock | Inventory record accuracy at cycle count | about 90% | 98% or more |
| Faster close | Month-end close duration | 15 working days | 5 working days |
| Receivables control | Days sales outstanding (DSO) | about 75 days | 55 days or less |
| Profitability visibility | P&L by branch and business line | Not available | Monthly by working day 5 |
| Sales pipeline | B2B opportunities tracked in CRM | None | 100% |
| Integrated showroom | POS sales posted to stock and accounting | Manual, weekly | Automatic, daily |

Baselines are discovery estimates (fictional project data). Targets are measured 6 months after go-live.

# 3. Scope

## 3.1 Modules in Scope

| Module | Processes | Main users |
| --- | --- | --- |
| CRM | Leads, opportunities, pipeline by sales team, activities, lost reasons | Sales Manager, reps |
| Sales | Quotations, orders, price lists, credit limit, margins, invoicing on delivery, installation services | Sales team |
| Point of Sale | Cairo showroom: barcode, serials, cash / card / customer account, session closing | Showroom |
| Purchase | RFQ, PO approval, vendor prices in EGP / USD, three-way match, reordering | Procurement |
| Inventory | 5 warehouses, multi-step routes, inter-warehouse resupply, serial numbers, landed costs, counts, scrap | Warehouses |
| Manufacturing | Multi-level BOMs, work centers, work orders, production cost, serial generation | Production |
| Accounting | Egypt localization, CoA, taxes, journals, banks, USD, analytic by line and branch, opening balances, reports | Finance |
| Employees / Time Off / Attendances | Departments, jobs, employees, users and access, leave, attendance | HR |
| Approvals | PO approval (standard) + approval rules per Approvals Matrix | Managers |

## 3.2 Locations in Scope

- Head office, Nasr City - management, finance, procurement, sales, HR, IT

- Cairo Warehouse (Main, CAW) - receipts with QC, assembly unit, Cairo showroom

- Alexandria (ALW), Mansoura (MAW), Ismailia (ISW), Asyut (ASW) warehouses - regional stock and delivery

## 3.3 Data Migration Scope

Chart of accounts, journals, analytic plans, departments, jobs, 36 employees, 18 customers, 14 vendors, price lists, 89 products, 11 BOMs, 5 warehouses, opening stock with 1,546 serial numbers, reordering rules, open opportunities and the opening journal entry at 1 Jan 2027. Transaction history stays in the legacy system (read-only).

## 3.4 Out of Scope

- Payroll (salary calculation) - phase 2 after the Egypt payroll localization is reviewed

- Egyptian e-invoice / e-receipt integration with the Tax Authority - phase 2

- eCommerce website and online payments

- Repairs / field service for warranty visits - phase 2

- Fleet management and vehicle costs

- WhatsApp integration and SMS notifications - phase 2

- Barcode app on handheld scanners - phase 2 (POS barcode scanning is in scope)

- External BI tools (e.g. Power BI) and data warehouse

## 3.5 Solution Approach

The instructor's guideline is about 70% Odoo standard, 10-15% workaround and 15-20% customization. The RTM baseline has 70 requirements: Standard 51 (73%), Workaround 8 (11%), Customization 11 (16%).

# 4. Methodology and Timeline

Phased Odoo implementation: database configuration, data migration set-up, database architecture, training preparation, testing / UAT, change management, cutover, go-live and hypercare.

| # | Phase | Start | End | Main outputs |
| --- | --- | --- | --- | --- |
| 1 | Initiation & Discovery | 04 Oct 2026 | 15 Oct 2026 | Kick-off, workshops, company profile, as-is processes, entity data collection |
| 2 | Analysis & Requirements | 11 Oct 2026 | 29 Oct 2026 | BRD, GAWF, RTM |
| 3 | Solution Design & Proposals | 25 Oct 2026 | 05 Nov 2026 | SSD, Technical Proposal (TPD), Financial Proposal (FPD) |
| 4 | Configuration & Data Migration | 08 Nov 2026 | 03 Dec 2026 | Database configuration, import files, customizations, integration tests |
| 5 | Testing / UAT | 06 Dec 2026 | 17 Dec 2026 | UAT cycles, defect fixing, UAT sign-off |
| 6 | Training & Change Management | 13 Dec 2026 | 24 Dec 2026 | Key-user and end-user training, user guides, communication |
| 7 | Cutover | 27 Dec 2026 | 31 Dec 2026 | Final balances, stock count, opening entry, go/no-go |
| 8 | Go-live & Hypercare | 01 Jan 2027 | 28 Jan 2027 | Go-live, daily support, issue log, handover |

Project calendar: Egyptian work week Sunday-Thursday. Go-live on the opening-balance date 1 Jan 2027 (Friday); first working day Sunday 3 Jan 2027.

## 4.1 Milestones and Sign-offs

| ID | Milestone | Date | Sign-off evidence |
| --- | --- | --- | --- |
| M1 | Project kick-off | 04 Oct 2026 | Kick-off minutes, team & roles |
| M2 | BRD sign-off | 22 Oct 2026 | Approved BRD |
| M3 | Solution & proposals sign-off | 05 Nov 2026 | Approved SSD, TPD, FPD (RTM baseline) |
| M4 | Configuration & data migration complete | 03 Dec 2026 | Configured test database with migrated data |
| M5 | UAT sign-off | 17 Dec 2026 | Signed UATD |
| M6 | Go-live | 01 Jan 2027 | Production live from fiscal-year start, opening balances posted; first working day Sun 3 Jan 2027 |
| M7 | Hypercare closure | 28 Jan 2027 | Hypercare report, handover to client admin |

# 5. Deliverables

| Deliverable | Phase | Owner |
| --- | --- | --- |
| Company Profile, Project Name & Scope, Team & Roles, Basic Database Configuration | 1 | Ahmed Fahmy / Omar ElSayed |
| Entity data (3 workbooks) and 27 import files | 1-4 | All consultants |
| BRD - Business Requirements Document | 2 | Ahmed Fahmy |
| RTM - Requirements Traceability Matrix | 2 | Noha Gamal |
| GAWF - Gap Analysis of Business Workflow | 2 | Mayada Salah |
| SSD - Solution Design Document | 3 | All consultants |
| TPD - Technical Proposal | 3 | Ahmed Fahmy |
| FPD - Financial Proposal | 3 | Ahmed Fahmy / Lobna Zanaty |
| UPD - Users Privileges Document | 4 | Omar ElSayed |
| UATD - User Acceptance Test Document | 5 | Noha Gamal |
| TD - Training Document; UDP - User Guides per Department | 6 | Omar ElSayed + module owners |
| Go-Live and Deployment Plan | 7 | Ahmed Fahmy |
| Presentation (PPTX / PDF) and demo video | 8 | All |

# 6. Assumptions and Constraints

- Odoo 19 Enterprise on Odoo Online / Odoo.sh with the Egypt fiscal localization

- Key users are available two days per week during analysis and UAT

- Beitak Smart supplies cleansed master data by the end of week 7

- Go-live date is fixed to the start of the fiscal year (1 Jan 2027)

- Opening USD rate 50.00 EGP and ~10% landed-cost uplift on imported items (project assumptions)

- Customizations are limited to Studio changes and reports listed in the RTM

# 7. Main Risks

| Risk | Level | Mitigation |
| --- | --- | --- |
| Late or poor-quality data from legacy files | High | Import templates issued in week 2; data owners named; validation rounds before go-live |
| Key users unavailable during UAT | Medium | UAT calendar agreed at kick-off; sponsor escalation |
| Scope creep (new reports and customizations) | Medium | Change-request process; customizations capped at about 20% of requirements |
| Users resist the new way of working | Medium | Key-user champions, hands-on training, user guides in simple language |
| Stock count differences at cutover | High | Full count 30-31 Dec; serial numbers labelled before count |
| Exchange-rate volatility affects opening values | Low | Rate fixed on cutover date and documented |

# 8. Approval

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Hany Mostafa | Project Sponsor - Beitak Smart |  |  |
| Ahmed Fahmy | Project Manager - Khomasi ERP |  |  |