## Index
Project Team and Roles
Smart Core - Beitak Smart Odoo ERP Implementation ¦ Version 1.0 ¦ 08 Oct 2026
Sheet | Content | Instructor requirement
Partner Team | Implementation team and responsibilities | Project Team & Roles
Client Team | Sponsor, client PM and key users | Responsible team in both parties
RACI | Who does what | Roles
Governance | Meetings and escalation | Project governance
Assumptions
Odoo version | Files target Odoo 18/19 field names (type=Goods + is_storable). On Odoo 17 replace 'type'+'is_storable' with 'detailed_type' = product.
Database | Designed for a NEW clean database with the Egypt fiscal localization. Importing into the old database will clash with existing account codes and products.
Exchange rate | USD/EGP = 50.00 on 2027-01-01. Project assumption, not an official CBE rate.
Landed costs | Cost of imported items = FOB price x 50 x 1.10 (about 10% for freight, duties, clearance and insurance). Assumption.
Sales prices | Sales prices are VAT-exclusive. VAT 14% comes from the Egypt localization default taxes.
Costing | AVCO + automated (perpetual) valuation on all stockable categories. Needed for Landed Costs.
Opening stock | Stock is loaded through Physical Inventory with accounting date 2027-01-01. Its counterpart is account 190100 Opening Stock Clearing, which the opening journal entry closes to zero.
Taxes | VAT 14% and withholding tax 1% / 2% / 3% (team decision). Rates, categories and thresholds must be reviewed by a tax specialist before go-live.
Personal data | All names, emails, phones, tax IDs and bank numbers are fictional placeholders (.example domains).

## Partner Team
Implementation Team - Khomasi ERP
Roles agreed by the team. Contact details are not published.
Member | Project Role | Modules | Responsibilities | Documents owned
Ahmed Fahmy | Project Manager & Manufacturing Consultant | Project management, Manufacturing | Plan and run the project, steering reports, scope and change control; BOMs, work centers, routings, production costing, scrap | Project Name & Scope, BRD, TPD, FPD, SSD manufacturing, Go-Live plan
Lobna Zanaty | Accounting Consultant | Accounting, Analytic, Taxes, Opening balances | CoA, taxes, journals, banks and cash, USD, analytic plans, opening balances, financial reports, month-end close | SSD accounting, FPD (costing support), User guide - Finance
Mayada Salah | Inventory Consultant | Inventory, Landed Costs | Warehouses, locations, routes, serial numbers, landed costs, replenishment, counts and scrap | GAWF, SSD inventory, User guide - Warehouse
Noha Gamal | Sales, CRM & POS Consultant | CRM, Sales, Point of Sale | Sales process, price lists, credit control, CRM pipeline, showroom POS | RTM, UATD, SSD sales/CRM/POS, User guide - Sales & Showroom
Omar ElSayed | HR, Purchase & Technical Consultant | Employees, Purchase, Users & Access, Data Migration | HR set-up, procurement and import flow, users and access rights, import files, database configuration, customizations | Basic Database Configuration, UPD, TD, SSD purchase/HR, Data migration files

## Client Team
Client Team - Beitak Smart
Key users approve requirements and test results for their area.
Name | Job | Project Role | Responsibilities
Hany Mostafa | General Manager | Project Sponsor | Final decisions, budget, sign-off of BRD, proposals, UAT and go-live
Omar Hassan | IT & ERP Administrator | Client Project Manager & System Administrator | Day-to-day coordination, data collection, user management after go-live
Rania Fathy | Finance Manager | Key User - Accounting | Accounting requirements, CoA, opening balances, UAT accounting
Sherif Nabil | Procurement & Import Manager | Key User - Purchase & Import | Procurement and import process, vendors, landed costs
Karim Adel | Sales Manager | Key User - Sales & CRM | Price lists, credit policy, sales teams, CRM
Salma Ashraf | Showroom Supervisor | Key User - Showroom (POS) | POS process, cash handling, refunds
Tamer Salah | Warehouse & Logistics Manager | Key User - Inventory | Warehouses, locations, counts, transfers
Mohamed Zaki | Production Manager | Key User - Manufacturing | BOMs, work centers, production flow
Dina Samir | HR Manager | Key User - HR | Departments, employees, time off

## RACI
RACI Matrix
R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | Sponsor | Client PM | Key Users | Partner PM | Consultants | End Users
Approve scope, budget and go-live | A | C | C | R | I | I
Project plan and status reports | I | C | I | A/R | C | -
Business requirements (BRD) | A | C | R | R | R | C
Gap analysis and RTM | I | C | C | A | R | -
Solution design (SSD) | I | C | C | A | R | -
Technical & financial proposals | A | C | I | R | C | -
Data collection and cleansing | I | A | R | C | C | C
Import files and data migration | I | C | C | A | R | -
Configuration and customizations | I | C | C | A | R | -
User access rights (UPD) | I | A | C | C | R | -
UAT execution and sign-off | A | R | R | C | C | C
Training and user guides | I | C | R | A | R | R
Cutover and stock count | A | R | R | C | C | R
Go-live decision | A | R | C | R | C | I
Hypercare support | I | C | C | A | R | C

## Governance
Governance and Communication
Meetings, participants and escalation path.
Forum | Participants | Frequency | Purpose
Steering committee | Sponsor, Client PM, Partner PM | Every 2 weeks | Progress, risks, decisions, change requests
Weekly status meeting | Client PM, key users, partner team | Weekly (Sunday) | Status report, issues, next week plan
Module workshops | Key user + module consultant | As planned in weeks 1-5 | Requirements, design decisions
Daily stand-up | Partner team | Daily, 15 minutes | Tasks, blockers
UAT review | Key users, consultants | Daily during UAT | Defects and retests
Escalation | Consultant > Partner PM > Client PM > Sponsor | Within 1 working day per level | Blocked decisions or resources