## Summary
Financial Proposal - Summary
Smart Core - Beitak Smart Odoo ERP Implementation ¦ Khomasi ERP ¦ v1.0 29 Oct 2026. Fictional project figures.
Item | EGP | US$
Implementation services (excl. VAT) | 981750
VAT on services | 137445
Implementation services (incl. VAT) | 1119195
Odoo subscription - year 1 (Custom, offer price) | 241200 | 4824
Total year-1 investment (excl. VAT) | 1222950
Yearly subscription from year 2 (list price estimate) | 295200 | 5904
Consultant days | 142

## Assumptions
Pricing Assumptions
Blue cells are inputs - change them and every sheet recalculates.
Item | Value | Note
PM day rate (EGP) | 7500 | Assumption - Egyptian market
Functional day rate (EGP) | 6000 | Assumption
Technical day rate (EGP) | 6500 | Assumption
Risk contingency | 10% | Share of services
VAT on services | 14% | To be confirmed by tax specialist
USD / EGP rate | 50 | Project assumption
Users | 30 | Users per Department sheet
Custom plan - offer (US$/user/month) | 13.4 | odoo.com/pricing, 25 Oct 2026
Custom plan - list (US$/user/month) | 16.4 | Struck-through price on pricing page
Standard plan (US$/user/month) | 7.25 | Comparison only - no Studio
Light user (US$/user/month) | 2.9 | Not used - conditions to confirm
Months per year | 12

## Services
Implementation Services
Days per workstream x day rate by role.
Workstream | Role | Days | Rate (EGP) | Amount (EGP)
Project management (planning, steering, reporting, change control) | Project Manager | 22 | 7500 | 165000
Discovery & analysis (workshops, BRD, GAWF, RTM) | Functional | 18 | 6000 | 108000
Solution design (SSD, TPD) | Functional | 8 | 6000 | 48000
Configuration - Accounting | Functional | 8 | 6000 | 48000
Configuration - Inventory & landed costs | Functional | 8 | 6000 | 48000
Configuration - Manufacturing | Functional | 6 | 6000 | 36000
Configuration - Sales & CRM | Functional | 5 | 6000 | 30000
Configuration - Point of Sale | Functional | 3 | 6000 | 18000
Configuration - Purchase | Functional | 4 | 6000 | 24000
Configuration - HR (Employees, Time Off, Attendances) | Functional | 3 | 6000 | 18000
Data migration (27 import files, validation, cutover loads) | Functional | 10 | 6000 | 60000
Customizations (11 items - RTM register) | Technical | 15 | 6500 | 97500
Testing & UAT support | Functional | 10 | 6000 | 60000
Training & user guides (TD, UDP) | Functional | 10 | 6000 | 60000
Cutover & go-live | Functional | 4 | 6000 | 24000
Hypercare (4 weeks after go-live) | Functional | 8 | 6000 | 48000
Subtotal |  | 142 |  | 892500
Risk contingency |  |  |  | 89250
Services total (excl. VAT) |  |  |  | 981750
VAT |  |  |  | 137445
Services total (incl. VAT) |  |  |  | 1119195

## Licenses
Odoo Subscription Options
Paid by Beitak Smart to Odoo in USD; converted at the assumed rate.
Option | US$/user/month | Users | Year (US$) | Year (EGP) | Fit
Custom - offer price (recommended) | 13.4 | 30 | 4824 | 241200 | Includes Studio
Custom - list price (renewal estimate) | 16.4 | 30 | 5904 | 295200 | Budget from year 2
Standard (comparison) | 7.25 | 30 | 2610 | 130500 | No Studio - customizations not possible
Light user (not used) | 2.9 | 0 | 0 | 0 | Conditions to confirm on odoo.com

## Milestones
Payment Milestones (services)
Percentages are inputs; amounts follow the services total.
Milestone | Planned date | % | Amount excl. VAT (EGP) | Amount incl. VAT (EGP)
M1 Project kick-off | 04 Oct 2026 | 20% | 196350 | 223839
M2 BRD sign-off | 22 Oct 2026 | 15% | 147262.5 | 167879.25
M3 Solution & proposals sign-off | 05 Nov 2026 | 15% | 147262.5 | 167879.25
M4 Configuration & data migration complete | 03 Dec 2026 | 20% | 196350 | 223839
M5 UAT sign-off | 17 Dec 2026 | 15% | 147262.5 | 167879.25
M6 Go-live | 01 Jan 2027 | 10% | 98175 | 111919.5
M7 Hypercare closure | 28 Jan 2027 | 5% | 49087.5 | 55959.75
Total |  | 100% | 981750 | 1119195
Check: total % = 100% |  | OK