Project Documents

Financial Proposal Document (FPD)

Smart Core - Beitak Smart Odoo ERP Implementation

| Client | Beitak Smart |
| --- | --- |
| Implementation partner | Khomasi ERP |
| Project | Smart Core - Beitak Smart Odoo ERP Implementation (BTK-ERP-01) |
| Document ID | BTK-DOC-06 |
| Version | 1.0 |
| Date | 29 Oct 2026 |
| Status | Submitted - for sign-off at M3 (05 Nov 2026) |
| Prepared by | Ahmed Fahmy (Project Manager), Lobna Zanaty (Accounting Consultant) |
| Approved by | Hany Mostafa - General Manager (Beitak Smart) |

# Document Control

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0 | 29 Oct 2026 | Ahmed Fahmy, Lobna Zanaty | Initial release |

| Distribution | Role |
| --- | --- |
| Hany Mostafa | Project Sponsor - Beitak Smart |
| Omar Hassan | Client Project Manager |
| Khomasi ERP project team | Implementation partner |

# 1. Summary

| Implementation services (excl. VAT) | 981,750.00 EGP |
| --- | --- |
| VAT 14% on services | 137,445.00 EGP |
| Implementation services (incl. VAT) | 1,119,195.00 EGP |
| Odoo subscription - year 1 (paid to Odoo) | 241,200.00 EGP (US$ 4,824.00) |
| Total year-1 investment (excl. VAT) | 1,222,950.00 EGP |
| Yearly subscription from year 2 (estimate) | 295,200.00 EGP (US$ 5,904.00) at list price |

Fictional project figures for the DEPI graduation project. Day rates and the exchange rate are assumptions. Final financial terms must be reviewed by the client's finance and legal advisors.

# 2. Pricing Assumptions

| Item | Value | Note |
| --- | --- | --- |
| Project Manager day rate | 7,500 EGP | Assumption - Egyptian market, Odoo partner |
| Functional consultant day rate | 6,000 EGP | Assumption |
| Technical consultant day rate | 6,500 EGP | Assumption (Studio, reports) |
| Risk contingency | 10% of services | Covers estimation risk |
| VAT on services | 14% | To be confirmed by tax specialist |
| USD / EGP rate | 50.00 | Project assumption; Odoo bills in USD |
| Odoo Custom plan | US$ 13.40 / user / month | odoo.com/pricing on 25 Oct 2026; list price US$ 16.40 shown struck through with a footnote |
| Users | 30 | Per Users per Department sheet |

# 3. Implementation Services

| Workstream | Role | Days | Rate (EGP) | Amount (EGP) |
| --- | --- | --- | --- | --- |
| Project management (planning, steering, reporting, change control) | Project Manager | 22 | 7,500 | 165,000.00 |
| Discovery & analysis (workshops, BRD, GAWF, RTM) | Functional | 18 | 6,000 | 108,000.00 |
| Solution design (SSD, TPD) | Functional | 8 | 6,000 | 48,000.00 |
| Configuration - Accounting | Functional | 8 | 6,000 | 48,000.00 |
| Configuration - Inventory & landed costs | Functional | 8 | 6,000 | 48,000.00 |
| Configuration - Manufacturing | Functional | 6 | 6,000 | 36,000.00 |
| Configuration - Sales & CRM | Functional | 5 | 6,000 | 30,000.00 |
| Configuration - Point of Sale | Functional | 3 | 6,000 | 18,000.00 |
| Configuration - Purchase | Functional | 4 | 6,000 | 24,000.00 |
| Configuration - HR (Employees, Time Off, Attendances) | Functional | 3 | 6,000 | 18,000.00 |
| Data migration (27 import files, validation, cutover loads) | Functional | 10 | 6,000 | 60,000.00 |
| Customizations (11 items - RTM register) | Technical | 15.0 | 6,500 | 97,500.00 |
| Testing & UAT support | Functional | 10 | 6,000 | 60,000.00 |
| Training & user guides (TD, UDP) | Functional | 10 | 6,000 | 60,000.00 |
| Cutover & go-live | Functional | 4 | 6,000 | 24,000.00 |
| Hypercare (4 weeks after go-live) | Functional | 8 | 6,000 | 48,000.00 |
| Subtotal |  | 142.0 |  | 892,500.00 |
| Risk contingency (10%) |  |  |  | 89,250.00 |
| Services total (excl. VAT) |  |  |  | 981,750.00 |
| VAT (14%) |  |  |  | 137,445.00 |
| Services total (incl. VAT) |  |  |  | 1,119,195.00 |

142.0 consultant days: Project Manager 22, functional 105, technical 15.0 (customization effort from the RTM register).

# 4. Odoo Subscription

| Option | Price (US$/user/month) | Users | Year (US$) | Year (EGP) | Fit |
| --- | --- | --- | --- | --- | --- |
| Custom - offer price (recommended) | 13.40 | 30 | 4,824.00 | 241,200.00 | Includes Studio needed for 11 customizations |
| Custom - list price (renewal estimate) | 16.40 | 30 | 5,904.00 | 295,200.00 | Used to budget year 2 onwards |
| Standard (comparison only) | 7.25 | 30 | 2,610.00 | 130,500.00 | No Studio - customizations not possible on Odoo Online |

- Subscription is contracted and paid by Beitak Smart directly to Odoo; taxes as invoiced by Odoo

- The struck-through prices and footnote on the pricing page mean the offer price has conditions (e.g. duration); confirm before signing

- Light User (US$ 2.90 / user / month) is not included in the baseline. Its conditions (which apps a light user can use) must be confirmed on odoo.com. All 30 users post transactions in core apps

- Saving option: showroom cashier and sales associate can sell with POS employee login under the supervisor's session, removing 2 paid users if the client accepts shared-device access

# 5. Payment Milestones (services)

| Milestone | Planned date | % | Amount excl. VAT (EGP) | Amount incl. VAT (EGP) |
| --- | --- | --- | --- | --- |
| M1 Project kick-off | 04 Oct 2026 | 20% | 196,350.00 | 223,839.00 |
| M2 BRD sign-off | 22 Oct 2026 | 15% | 147,262.50 | 167,879.25 |
| M3 Solution & proposals sign-off | 05 Nov 2026 | 15% | 147,262.50 | 167,879.25 |
| M4 Configuration & data migration complete | 03 Dec 2026 | 20% | 196,350.00 | 223,839.00 |
| M5 UAT sign-off | 17 Dec 2026 | 15% | 147,262.50 | 167,879.25 |
| M6 Go-live | 01 Jan 2027 | 10% | 98,175.00 | 111,919.50 |
| M7 Hypercare closure | 28 Jan 2027 | 5% | 49,087.50 | 55,959.75 |
| Total |  | 100% | 981,750.00 | 1,119,195.00 |

Invoices are issued on each milestone sign-off and paid within 15 days.

# 6. Optional Services (not included)

| Service | Basis | Indicative price (excl. VAT) |
| --- | --- | --- |
| Monthly support after hypercare | 4 functional days per month, 6-month minimum | 24,000 EGP / month |
| Change requests | Per approved estimate | Day rates in section 2 |
| Additional training sessions | Per half day | 3,000 EGP / session |
| Phase 2 (e-invoice, repairs, WhatsApp, barcode app) | Separate proposal | Quoted after phase 1 |

# 7. Terms and Conditions

- Prices in EGP, excluding VAT. Offer valid until 28 Nov 2026.

- Fixed price for the scope in the BRD, RTM and SSD; anything else follows the change-request process.

- Beitak Smart provides key users, cleansed data and timely approvals as listed in the TPD; delays may move milestones.

- Defects in delivered configuration found during hypercare are fixed at no extra cost.

- Customizations and documents become the property of Beitak Smart after final payment.

- Both parties keep each other's information confidential.

- The Odoo subscription is a separate contract between Beitak Smart and Odoo; USD prices are converted at the rate on the invoice date.

- This proposal is fictional project material and is not legal or tax advice.

# 8. Approval

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Hany Mostafa | Project Sponsor - Beitak Smart |  |  |
| Rania Fathy | Finance Manager - Beitak Smart |  |  |
| Ahmed Fahmy | Project Manager - Khomasi ERP |  |  |