## Index
Requirements Traceability Matrix (RTM)
Smart Core - Beitak Smart Odoo ERP Implementation ¦ Version 1.0 ¦ 25 Oct 2026
Sheet | Content | Instructor requirement
RTM | 70 requirements traced end to end | RTM
Fit-Gap Summary | Standard / Workaround / Customization by module | Execute modules 70 / 10-15 / 15-20
Pain Point Coverage | Pain points vs requirements | BRD traceability
Customization Register | Customizations and effort | Input to SSD and FPD
Workaround Register | Workarounds | Input to SSD and training
Assumptions
Odoo version | Files target Odoo 18/19 field names (type=Goods + is_storable). On Odoo 17 replace 'type'+'is_storable' with 'detailed_type' = product.
Database | Designed for a NEW clean database with the Egypt fiscal localization. Importing into the old database will clash with existing account codes and products.
Exchange rate | USD/EGP = 50.00 on 2027-01-01. Project assumption, not an official CBE rate.
Landed costs | Cost of imported items = FOB price x 50 x 1.10 (about 10% for freight, duties, clearance and insurance). Assumption.
Sales prices | Sales prices are VAT-exclusive. VAT 14% comes from the Egypt localization default taxes.
Costing | AVCO + automated (perpetual) valuation on all stockable categories. Needed for Landed Costs.
Opening stock | Stock is loaded through Physical Inventory with accounting date 2027-01-01. Its counterpart is account 190100 Opening Stock Clearing, which the opening journal entry closes to zero.
Taxes | VAT 14% and withholding tax 1% / 2% / 3% (team decision). Rates, categories and thresholds must be reviewed by a tax specialist before go-live.
Personal data | All names, emails, phones, tax IDs and bank numbers are fictional placeholders (.example domains).

## RTM
Requirements Traceability Matrix
Baseline v1.0 25 Oct 2026 - for sign-off at M3. Each BRD requirement is traced to its Odoo solution, SSD section, import file, owner and UAT test case.
Req. ID | Module | Requirement | Priority | Source (pain point) | Fit / Gap | Odoo Solution | SSD Ref. | Import File | Owner | UAT Test Case | Status
BR-CRM-01 | CRM | Capture leads and opportunities from exhibitions, phone, WhatsApp and website in one pipeline (New > Qualified > Proposition > Won / Lost) | Must | PP-08 | Standard | CRM pipeline, stages, lead sources (UTM) | SSD 3.1 | 26 | Noha Gamal | TC-CRM-01 | Planned
BR-CRM-02 | CRM | Assign opportunities to regional sales teams; managers see their team, reps see only their own | Must | PP-08, PP-14 | Standard | Sales teams + access 'Own documents only' | SSD 3.1 | 11 | Noha Gamal | TC-CRM-02 | Planned
BR-CRM-03 | CRM | Schedule follow-up activities and log calls and meetings per opportunity | Should | PP-08 | Standard | Activities and chatter | SSD 3.1 | - | Noha Gamal | TC-CRM-03 | Planned
BR-CRM-04 | CRM | Record lost reasons and analyse win / loss | Should | PP-08 | Standard | Lost reasons + pipeline analysis | SSD 3.1 | - | Noha Gamal | TC-CRM-04 | Planned
BR-CRM-05 | CRM | Monthly revenue target per salesperson with achievement % | Should | PP-09 | Customization | Target field per salesperson + achievement report (Studio) | SSD 3.1 | - | Noha Gamal | TC-CRM-05 | Planned
BR-SAL-01 | Sales | Quotations and sales orders use customer price lists (retail, wholesale, distributors, key accounts) with quantity breaks | Must | PP-02 | Standard | Price lists with advanced rules | SSD 3.2 | 10, 12 | Noha Gamal | TC-SAL-01 | Planned
BR-SAL-02 | Sales | When a list price changes, all price lists update automatically | Must | PP-02 | Standard | Percentage rules based on list price | SSD 3.2 | 10 | Noha Gamal | TC-SAL-02 | Planned
BR-SAL-03 | Sales | Warn the user when a customer's exposure exceeds the credit limit | Must | PP-07 | Standard | Sales Credit Limit (warning on order and invoice) | SSD 3.2 | 12 | Noha Gamal | TC-SAL-03 | Planned
BR-SAL-04 | Sales | Block confirmation of orders above credit limit unless the Finance Manager approves | Should | PP-07 | Customization | Approval check on order confirmation (Studio approval rule / small module) | SSD 3.2 | - | Noha Gamal | TC-SAL-04 | Planned
BR-SAL-05 | Sales | Discounts above 10% require Sales Manager approval | Should | PP-02 | Customization | Approval rule on discount (Studio) | SSD 3.2 | - | Noha Gamal | TC-SAL-05 | Planned
BR-SAL-06 | Sales | Invoice customers on delivered quantities only | Must | PP-10 | Standard | Invoicing policy: delivered quantities | SSD 3.2 | 17 | Noha Gamal | TC-SAL-06 | Planned
BR-SAL-07 | Sales | Sell installation services together with appliances | Could | PP-09 | Standard | Service products on sales orders | SSD 3.2 | 17 | Noha Gamal | TC-SAL-07 | Planned
BR-SAL-08 | Sales | Bilingual (Arabic / English) tax invoice showing tax registration numbers | Must | Compliance | Customization | Customized invoice report (QWeb) | SSD 3.2 | - | Noha Gamal | TC-SAL-08 | Planned
BR-SAL-09 | Sales | Gross margin per order line and product visible to managers | Should | PP-01, PP-09 | Standard | Margins setting + sales analysis | SSD 3.2 | - | Noha Gamal | TC-SAL-09 | Planned
BR-SAL-10 | Sales | Sales commission report per salesperson based on collected invoices | Could | PP-09 | Customization | Custom report (collected invoices x commission rate) | SSD 3.2 | - | Noha Gamal | TC-SAL-10 | Planned
BR-POS-01 | POS | Showroom sales through POS with barcode scanning, linked to stock and accounting | Must | PP-11 | Standard | Point of Sale linked to CAW warehouse | SSD 3.3 | 16, 17 | Noha Gamal | TC-POS-01 | Planned
BR-POS-02 | POS | Payment by cash, card and customer account | Must | PP-11 | Standard | POS payment methods (POSCS, NBEG, Customer Account) | SSD 3.3 | 02 | Noha Gamal | TC-POS-02 | Planned
BR-POS-03 | POS | Capture the serial number of each appliance sold in POS | Must | PP-06 | Standard | Lot / serial selection in POS | SSD 3.3 | 23 | Noha Gamal | TC-POS-03 | Planned
BR-POS-04 | POS | Daily session closing with cash count and posting of differences | Must | PP-11 | Standard | POS session closing, cash difference accounts | SSD 3.3 | - | Noha Gamal | TC-POS-04 | Planned
BR-POS-05 | POS | Refunds only by the Showroom Supervisor | Should | PP-14 | Workaround | Refunds done by POS Administrator; cashiers use employee login | SSD 3.3 | - | Noha Gamal | TC-POS-05 | Planned
BR-PUR-01 | Purchase | RFQs and POs with vendor prices and lead times; overseas vendors in USD | Must | PP-03 | Standard | Vendor price lists, multi-currency | SSD 3.4 | 13, 17 | Omar ElSayed | TC-PUR-01 | Planned
BR-PUR-02 | Purchase | POs above 250,000 EGP need Procurement Manager approval | Must | PP-12 | Standard | Purchase Order Approval (two-step validation) | SSD 3.4 | - | Omar ElSayed | TC-PUR-02 | Planned
BR-PUR-03 | Purchase | All overseas (USD) POs approved by the General Manager | Should | PP-12 | Workaround | GM confirms overseas POs with Purchase Administrator rights | SSD 3.4 | - | Omar ElSayed | TC-PUR-03 | Planned
BR-PUR-04 | Purchase | Vendor bills matched to received quantities (three-way match) | Must | PP-10 | Standard | Bill control: received quantities | SSD 3.4 | - | Omar ElSayed | TC-PUR-04 | Planned
BR-PUR-05 | Purchase | Allocate freight, customs duties, clearance and insurance to the cost of imported items | Must | PP-01 | Standard | Landed costs (4 landed-cost products, clearing accounts 1301xx) | SSD 3.4 | 17 | Omar ElSayed | TC-PUR-05 | Planned
BR-PUR-06 | Purchase | Track container number, bill of lading and ETA on import POs and receipts | Should | PP-01, PP-03 | Customization | Custom fields on PO and receipt (Studio) | SSD 3.4 | - | Omar ElSayed | TC-PUR-06 | Planned
BR-PUR-07 | Purchase | Purchase analysis by vendor, product and currency | Should | PP-03 | Standard | Purchase analysis report | SSD 3.4 | - | Omar ElSayed | TC-PUR-07 | Planned
BR-PUR-08 | Purchase | Automatic RFQs from min / max reordering rules | Must | PP-03 | Standard | Reordering rules + Buy route | SSD 3.4 | 25 | Omar ElSayed | TC-PUR-08 | Planned
BR-PUR-09 | Purchase | Import shipment cost sheet: FOB, freight, duties, clearance and landed cost per unit per container | Should | PP-01 | Customization | Custom report on landed costs | SSD 3.4 | - | Omar ElSayed | TC-PUR-09 | Planned
BR-INV-01 | Inventory | Five warehouses with storage locations (floors, raw materials store, finished goods, showroom) | Must | PP-04 | Standard | Warehouses and storage locations | SSD 3.5 | 21, 22 | Mayada Salah | TC-INV-01 | Planned
BR-INV-02 | Inventory | Real-time stock by product, location and warehouse visible to sales | Must | PP-04 | Standard | Stock reports, forecasted quantities on order lines | SSD 3.5 | 24 | Mayada Salah | TC-INV-02 | Planned
BR-INV-03 | Inventory | Cairo receipts in three steps with quality control; branches in one step | Must | PP-04 | Standard | Multi-step routes | SSD 3.5 | 21 | Mayada Salah | TC-INV-03 | Planned
BR-INV-04 | Inventory | Deliveries: Cairo pick-pack-ship, branches pick-ship | Should | PP-04 | Standard | Multi-step routes | SSD 3.5 | 21 | Mayada Salah | TC-INV-04 | Planned
BR-INV-05 | Inventory | Branches replenished from Cairo through inter-warehouse transfers | Must | PP-03, PP-04 | Standard | Resupply routes between warehouses | SSD 3.5 | 21 | Mayada Salah | TC-INV-05 | Planned
BR-INV-06 | Inventory | Serial-number tracking for all appliances from receipt to delivery and returns | Must | PP-06 | Standard | Lots & serial numbers | SSD 3.5 | 17, 23 | Mayada Salah | TC-INV-06 | Planned
BR-INV-07 | Inventory | Warranty end date per serial number calculated from the delivery date | Should | PP-06 | Customization | Warranty months on product + computed field on serial (Studio) | SSD 3.5 | - | Mayada Salah | TC-INV-07 | Planned
BR-INV-08 | Inventory | AVCO valuation with automatic accounting entries | Must | PP-01, PP-10 | Standard | Automated valuation on product categories | SSD 3.5 | 15 | Mayada Salah | TC-INV-08 | Planned
BR-INV-09 | Inventory | Cycle counts; only the Warehouse Manager applies adjustments | Must | PP-04, PP-14 | Standard | Physical Inventory; Apply limited to Inventory Administrator | SSD 3.5 | - | Mayada Salah | TC-INV-09 | Planned
BR-INV-10 | Inventory | Scrap recording; scrap above 10,000 EGP reviewed by the Production Manager | Should | PP-05 | Workaround | Scrap orders + weekly scrap report review | SSD 3.5 | - | Mayada Salah | TC-INV-10 | Planned
BR-INV-11 | Inventory | Customer returns go to quality control with serial check | Should | PP-06 | Standard | Return transfers to QC location | SSD 3.5 | - | Mayada Salah | TC-INV-11 | Planned
BR-MRP-01 | Manufacturing | Multi-level BOMs for assembled products (fan with control-board sub-assembly) | Must | PP-05 | Standard | Bills of materials | SSD 3.6 | 19 | Ahmed Fahmy | TC-MRP-01 | Planned
BR-MRP-02 | Manufacturing | Work orders by work center with time tracking | Must | PP-05 | Standard | Work orders, work centers, operations | SSD 3.6 | 18, 20 | Ahmed Fahmy | TC-MRP-02 | Planned
BR-MRP-03 | Manufacturing | Product cost = components + labour and overhead per work center | Must | PP-05, PP-01 | Standard | AVCO + work center cost per hour | SSD 3.6 | 18 | Ahmed Fahmy | TC-MRP-03 | Planned
BR-MRP-04 | Manufacturing | Automatic manufacturing orders from reordering rules | Should | PP-03 | Standard | Reordering rules + Manufacture route | SSD 3.6 | 25 | Ahmed Fahmy | TC-MRP-04 | Planned
BR-MRP-05 | Manufacturing | Generate serial numbers for finished fans at production | Must | PP-06 | Standard | Serial generation on manufacturing order | SSD 3.6 | - | Ahmed Fahmy | TC-MRP-05 | Planned
BR-MRP-06 | Manufacturing | Record component scrap during production | Should | PP-05 | Standard | Scrap from manufacturing order | SSD 3.6 | - | Ahmed Fahmy | TC-MRP-06 | Planned
BR-MRP-07 | Manufacturing | Quality check before finished goods move to stock | Should | PP-05 | Workaround | QC operation in the routing + inspector sign-off (Quality app not in scope) | SSD 3.6 | 20 | Ahmed Fahmy | TC-MRP-07 | Planned
BR-MRP-08 | Manufacturing | Production performance: planned vs actual time and cost variance | Could | PP-05 | Workaround | Work order analysis + MO cost comparison | SSD 3.6 | - | Ahmed Fahmy | TC-MRP-08 | Planned
BR-ACC-01 | Accounting | Egyptian chart of accounts with inventory, revenue and COGS by product line | Must | PP-09 | Standard | Egypt localization + 61 Beitak Smart accounts | SSD 3.7 | 01 | Lobna Zanaty | TC-ACC-01 | Planned
BR-ACC-02 | Accounting | Egyptian VAT 14% on sales and purchases; withholding tax 1% / 2% / 3% on purchases (rates reviewed by a tax specialist) | Must | Compliance | Standard | Egypt localization taxes | SSD 3.7 | - | Lobna Zanaty | TC-ACC-02 | Planned
BR-ACC-03 | Accounting | USD transactions with exchange differences posted on payment | Must | PP-02 | Standard | Multi-currency | SSD 3.7 | - | Lobna Zanaty | TC-ACC-03 | Planned
BR-ACC-04 | Accounting | 4 bank and 4 cash journals with reconciliation | Must | PP-10 | Standard | Bank / cash journals, reconciliation | SSD 3.7 | 02 | Lobna Zanaty | TC-ACC-04 | Planned
BR-ACC-05 | Accounting | Post-dated cheques received and issued tracked until collection | Must | PP-07 | Workaround | Notes receivable / payable accounts (110300, 212100) with maturity date in reference | SSD 3.7 | 27 | Lobna Zanaty | TC-ACC-05 | Planned
BR-ACC-06 | Accounting | Aged receivable / payable and customer statements | Must | PP-07 | Standard | Aged partner balance, follow-up | SSD 3.7 | - | Lobna Zanaty | TC-ACC-06 | Planned
BR-ACC-07 | Accounting | Profitability by business line and branch | Must | PP-09 | Standard | Analytic plans + distribution models | SSD 3.7 | 03, 04 | Lobna Zanaty | TC-ACC-07 | Planned
BR-ACC-08 | Accounting | Payments above 500,000 EGP posted only by the Finance Manager | Should | PP-12 | Workaround | Treasurer drafts payments; Finance Manager posts | SSD 3.7 | - | Lobna Zanaty | TC-ACC-08 | Planned
BR-ACC-09 | Accounting | Month-end close within 5 working days with lock dates | Must | PP-10 | Standard | Lock dates, reconciliation, closing checklist | SSD 3.7 | - | Lobna Zanaty | TC-ACC-09 | Planned
BR-ACC-10 | Accounting | Opening balances by account and partner as at 1 Jan 2027 | Must | PP-10 | Standard | Opening journal entry import | SSD 3.7 | 27 | Lobna Zanaty | TC-ACC-10 | Planned
BR-ACC-11 | Accounting | Trial balance, P&L, balance sheet and VAT report | Must | PP-10 | Standard | Accounting reports (Enterprise) | SSD 3.7 | - | Lobna Zanaty | TC-ACC-11 | Planned
BR-ACC-12 | Accounting | Inventory valuation report reconciles with GL inventory accounts | Must | PP-01 | Standard | Stock valuation report vs 1201xx accounts | SSD 3.7 | - | Lobna Zanaty | TC-ACC-12 | Planned
BR-HR-01 | HR | Employee records with departments, job positions and managers | Must | PP-13 | Standard | Employees app | SSD 3.8 | 05-08 | Omar ElSayed | TC-HR-01 | Planned
BR-HR-02 | HR | Leave requests approved by the direct manager | Should | PP-13 | Standard | Time Off | SSD 3.8 | - | Omar ElSayed | TC-HR-02 | Planned
BR-HR-03 | HR | Attendance check-in / out for warehouse and production staff | Could | PP-13 | Standard | Attendances (kiosk mode) | SSD 3.8 | - | Omar ElSayed | TC-HR-03 | Planned
BR-HR-04 | HR | Each user linked to an employee with role-based access rights | Must | PP-14 | Standard | Users created from employees + access groups | SSD 3.8 | 07 | Omar ElSayed | TC-HR-04 | Planned
BR-GEN-01 | Cross-functional | Migrate master data and opening stock with serial numbers | Must | PP-10 | Standard | Import files 01-27 | SSD 3.9 | 01-27 | Omar ElSayed | TC-GEN-01 | Planned
BR-GEN-02 | Cross-functional | Audit trail of changes on key documents | Must | PP-12 | Standard | Chatter tracking | SSD 3.9 | - | Omar ElSayed | TC-GEN-02 | Planned
BR-GEN-03 | Cross-functional | History of product price changes | Should | PP-02 | Customization | Field tracking on sales price and cost (Studio) | SSD 3.9 | - | Omar ElSayed | TC-GEN-03 | Planned
BR-GEN-04 | Cross-functional | Management dashboard: sales vs target, stock value, overdue receivables | Should | PP-09 | Workaround | Standard reports saved to a dashboard / spreadsheet | SSD 3.9 | - | Omar ElSayed | TC-GEN-04 | Planned
BR-GEN-05 | Cross-functional | Assign delivery drivers and print a daily trip sheet | Could | PP-04 | Customization | Driver field on delivery + trip-sheet report | SSD 3.9 | - | Omar ElSayed | TC-GEN-05 | Planned
BR-GEN-06 | Cross-functional | Bilingual delivery note and transfer documents with serial numbers and signature box | Should | PP-06 | Customization | Customized delivery report (QWeb) | SSD 3.9 | - | Omar ElSayed | TC-GEN-06 | Planned

## Fit-Gap Summary
Fit / Gap Summary
Instructor target: Standard ~70%, Workaround 10-15%, Customization 15-20%.
Module | Standard | Workaround | Customization | Total
CRM
Sales
POS
Purchase
Inventory
Manufacturing
Accounting
HR
Cross-functional
Total
Share of total
Target | about 70% | 10% - 15% | 15% - 20%
Within target?

## Pain Point Coverage
Pain Point Coverage
Every pain point from the BRD is covered by at least one requirement.
Pain Point | Description | Impact | Requirements | Requirement IDs
PP-01 | Landed costs (freight, duties, clearance, insurance) are not added to item cost; margins are overstated | High |  | BR-SAL-09, BR-PUR-05, BR-PUR-06, BR-PUR-09, BR-INV-08, BR-MRP-03, BR-ACC-12
PP-02 | Price lists are updated manually in Excel after USD changes; customers get outdated or inconsistent prices | High |  | BR-SAL-01, BR-SAL-02, BR-SAL-05, BR-ACC-03, BR-GEN-03
PP-03 | Frequent stock-outs on fast movers and overstock on slow items; no min/max rules; long import lead times | High |  | BR-PUR-01, BR-PUR-06, BR-PUR-07, BR-PUR-08, BR-INV-05, BR-MRP-04
PP-04 | No real-time stock visibility across 5 warehouses and the showroom; sales confirm availability by phone | High |  | BR-INV-01, BR-INV-02, BR-INV-03, BR-INV-04, BR-INV-05, BR-INV-09, BR-GEN-05
PP-05 | Cost of assembled products is unknown; component consumption, labour and scrap are not recorded | High |  | BR-INV-10, BR-MRP-01, BR-MRP-02, BR-MRP-03, BR-MRP-06, BR-MRP-07, BR-MRP-08
PP-06 | No serial-number traceability for warranty claims and customer returns | Medium |  | BR-POS-03, BR-INV-06, BR-INV-07, BR-INV-11, BR-MRP-05, BR-GEN-06
PP-07 | Receivables and post-dated cheques tracked in Excel; credit limits not enforced; overdue balances grow | High |  | BR-SAL-03, BR-SAL-04, BR-ACC-05, BR-ACC-06
PP-08 | Leads from exhibitions, phone and WhatsApp are lost; no pipeline or follow-up | Medium |  | BR-CRM-01, BR-CRM-02, BR-CRM-03, BR-CRM-04
PP-09 | No profitability by business line (trading, manufacturing, services) or by branch | High |  | BR-CRM-05, BR-SAL-07, BR-SAL-09, BR-SAL-10, BR-ACC-01, BR-ACC-07, BR-GEN-04
PP-10 | Month-end close takes about 15 working days; data re-keyed between separate files and the legacy accounting package | High |  | BR-SAL-06, BR-PUR-04, BR-INV-08, BR-ACC-04, BR-ACC-09, BR-ACC-10, BR-ACC-11, BR-GEN-01
PP-11 | Showroom uses a standalone cashier program; stock and accounting are updated manually | Medium |  | BR-POS-01, BR-POS-02, BR-POS-04
PP-12 | Purchase and payment approvals happen on paper or WhatsApp with no audit trail | Medium |  | BR-PUR-02, BR-PUR-03, BR-ACC-08, BR-GEN-02
PP-13 | Employee data is scattered; leave requests are on paper | Low |  | BR-HR-01, BR-HR-02, BR-HR-03
PP-14 | Shared logins and no segregation of duties in current tools | Medium |  | BR-CRM-02, BR-POS-05, BR-INV-09, BR-HR-04

## Customization Register
Customization Register
Estimated effort in consultant days (input for the Financial Proposal).
Req. ID | Module | Requirement | Design | Technique | Effort (days)
BR-CRM-05 | CRM | Monthly revenue target per salesperson with achievement % | Target field per salesperson + achievement report (Studio) | Studio | 1
BR-SAL-04 | Sales | Block confirmation of orders above credit limit unless the Finance Manager approves | Approval check on order confirmation (Studio approval rule / small module) | Studio approval rule | 1.5
BR-SAL-05 | Sales | Discounts above 10% require Sales Manager approval | Approval rule on discount (Studio) | Studio approval rule | 1
BR-SAL-08 | Sales | Bilingual (Arabic / English) tax invoice showing tax registration numbers | Customized invoice report (QWeb) | QWeb report | 2
BR-SAL-10 | Sales | Sales commission report per salesperson based on collected invoices | Custom report (collected invoices x commission rate) | Custom report | 2
BR-PUR-06 | Purchase | Track container number, bill of lading and ETA on import POs and receipts | Custom fields on PO and receipt (Studio) | Studio fields | 0.5
BR-PUR-09 | Purchase | Import shipment cost sheet: FOB, freight, duties, clearance and landed cost per unit per container | Custom report on landed costs | Custom report | 2
BR-INV-07 | Inventory | Warranty end date per serial number calculated from the delivery date | Warranty months on product + computed field on serial (Studio) | Studio computed field | 1.5
BR-GEN-03 | Cross-functional | History of product price changes | Field tracking on sales price and cost (Studio) | Studio tracking | 0.5
BR-GEN-05 | Cross-functional | Assign delivery drivers and print a daily trip sheet | Driver field on delivery + trip-sheet report | Studio field + report | 1.5
BR-GEN-06 | Cross-functional | Bilingual delivery note and transfer documents with serial numbers and signature box | Customized delivery report (QWeb) | QWeb report | 1.5
Total

## Workaround Register
Workaround Register
Needs met with standard features used in a specific way - documented for training and the user guides.
Req. ID | Module | Requirement | Workaround
BR-POS-05 | POS | Refunds only by the Showroom Supervisor | Refunds done by POS Administrator; cashiers use employee login
BR-PUR-03 | Purchase | All overseas (USD) POs approved by the General Manager | GM confirms overseas POs with Purchase Administrator rights
BR-INV-10 | Inventory | Scrap recording; scrap above 10,000 EGP reviewed by the Production Manager | Scrap orders + weekly scrap report review
BR-MRP-07 | Manufacturing | Quality check before finished goods move to stock | QC operation in the routing + inspector sign-off (Quality app not in scope)
BR-MRP-08 | Manufacturing | Production performance: planned vs actual time and cost variance | Work order analysis + MO cost comparison
BR-ACC-05 | Accounting | Post-dated cheques received and issued tracked until collection | Notes receivable / payable accounts (110300, 212100) with maturity date in reference
BR-ACC-08 | Accounting | Payments above 500,000 EGP posted only by the Finance Manager | Treasurer drafts payments; Finance Manager posts
BR-GEN-04 | Cross-functional | Management dashboard: sales vs target, stock value, overdue receivables | Standard reports saved to a dashboard / spreadsheet