Project Documents

Training Document (TD)

Smart Core - Beitak Smart Odoo ERP Implementation

| Client | Beitak Smart |
| --- | --- |
| Implementation partner | Khomasi ERP |
| Project | Smart Core - Beitak Smart Odoo ERP Implementation (BTK-ERP-01) |
| Document ID | BTK-DOC-09 |
| Version | 1.0 |
| Date | 17 Dec 2026 |
| Status | Approved |
| Prepared by | Omar ElSayed (HR, Purchase & Technical Consultant) |
| Approved by | Hany Mostafa - General Manager (Beitak Smart) |

# Document Control

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0 | 17 Dec 2026 | Omar ElSayed | Initial release |

| Distribution | Role |
| --- | --- |
| Hany Mostafa | Project Sponsor - Beitak Smart |
| Omar Hassan | Client Project Manager |
| Khomasi ERP project team | Implementation partner |

# 1. Objective and Approach

Train every Beitak Smart user to run their daily work in Odoo before go-live. The approach is train-the-trainer: key users are trained first during UAT, then end users are trained by module with hands-on exercises in the test database.

| Users to train | 30 users across 10 departments |
| --- | --- |
| Sessions | 10 sessions, 33 hours of material |
| Environment | Test database with migrated data (same data as UAT) |
| Language | Arabic delivery, English screens; guides bilingual where needed |
| Group size | Maximum 10 users per session |
| Materials | Slides, user guides per department (UDP), quick reference cards, exercises |

# 2. Training Needs by Department

| Department | Users | Sessions | Focus |
| --- | --- | --- | --- |
| General Management | 1 | T-01, T-10 | Approvals and dashboards |
| Finance & Accounting | 4 | T-01, T-07, T-08 | Daily accounting and month-end close |
| Procurement & Import | 3 | T-01, T-04 | Approval flow and landed costs |
| Sales | 7 | T-01, T-02 | Pipeline, pricing, credit control |
| Showroom & Retail | 3 | T-01, T-03 | POS and cash handling |
| Warehouse & Logistics | 6 | T-01, T-05 | Transfers, serials, counts |
| Production | 2 | T-01, T-06 | Work orders and costing |
| Quality Control | 1 | T-01, T-06 | QC step before stock |
| Human Resources | 2 | T-01, T-09 | Employee records and leave |
| IT & ERP | 1 | T-01, T-10 | Users, imports, support |

# 3. Session Plan

| ID | Session | Audience | Trainer | Hours | Topics |
| --- | --- | --- | --- | --- | --- |
| T-01 | Odoo basics for all users | All 30 users (3 groups of 10) | Omar ElSayed | 2 | Logging in, navigation, list and form views, filters and grouping, favourites, chatter and activities, attachments, exporting to Excel, changing own password |
| T-02 | Sales and CRM | Sales Manager, Key Account Manager, 5 reps | Noha Gamal | 4 | Pipeline and activities, lost reasons, quotations and price lists, credit-limit warning and approval, discount approval, delivery and invoicing, margins, sales reports |
| T-03 | Point of Sale | Supervisor, cashier, sales associate | Noha Gamal | 3 | Opening a session, barcode scanning, selecting serial numbers, payment methods, customer account sales, refunds (supervisor), closing with cash count, daily deposit |
| T-04 | Purchase and import | Procurement Manager, import specialist, buyer, GM | Omar ElSayed | 4 | RFQ and PO, approval flow, vendor prices in EGP and USD, container and ETA fields, receipts with QC, three-way match, landed costs, shipment cost sheet, reordering rules |
| T-05 | Inventory and warehouses | Warehouse Manager, 5 keepers | Mayada Salah | 4 | Receipts, put-away, serial numbers, deliveries and the step routes, branch transfers, returns to QC, cycle counts, scrap, replenishment report |
| T-06 | Manufacturing | Production Manager, supervisor, QC inspector, technicians | Ahmed Fahmy | 4 | BOMs and sub-assemblies, manufacturing orders, work orders and timers, component consumption, scrap, serial generation, QC step, production cost |
| T-07 | Accounting - daily | Finance Manager, 2 accountants, treasurer | Lobna Zanaty | 4 | Customer invoices and vendor bills, taxes (VAT and WHT), payments and post-dated cheques, bank and cash reconciliation, POS session entries, aged reports |
| T-08 | Accounting - periodic | Finance Manager, senior accountant | Lobna Zanaty | 3 | Landed-cost review, stock valuation vs GL, analytic reports by branch and business line, VAT return, lock dates, month-end checklist, financial statements |
| T-09 | HR | HR Manager, HR specialist, all managers (leave approval) | Omar ElSayed | 2 | Employee records, job positions, time-off requests and approval, attendance kiosk, employee self-service |
| T-10 | Administration and reporting | System Administrator, GM, department managers | Omar ElSayed | 3 | Users and access rights, archiving leavers, imports, saved filters and dashboards, standard reports, raising support issues |

# 4. Schedule

| When | What | Who | Note |
| --- | --- | --- | --- |
| Week 11 | Key-user training (train the trainer) | T-02 to T-08 with the key user of each module | During UAT; key users then help their teams |
| Week 12, Sun-Mon | T-01 Odoo basics | 3 groups of 10 users | Head office training room |
| Week 12, Tue-Thu | T-02, T-03, T-04, T-05 | Sales, showroom, procurement, warehouses | Hands-on in the test database |
| Week 13, Sun-Mon | T-06, T-07, T-08, T-09, T-10 | Production, finance, HR, administration | Hands-on in the test database |
| Week 13, Tue | Open clinic | Anyone with questions | Drop-in with consultants |
| Hypercare (Jan) | Refresher sessions on request | Teams with open questions | Remote, 1 hour each |

# 5. Materials

| Material | Owner | Used in |
| --- | --- | --- |
| Slides, quick reference card | Omar ElSayed | T-01 |
| User guide - Sales, test scripts | Noha Gamal | T-02 |
| User guide - Showroom | Noha Gamal | T-03 |
| User guide - Procurement | Omar ElSayed | T-04 |
| User guide - Warehouse | Mayada Salah | T-05 |
| User guide - Production | Ahmed Fahmy | T-06 |
| User guide - Finance | Lobna Zanaty | T-07 |
| User guide - Finance, closing checklist | Lobna Zanaty | T-08 |
| User guide - HR | Omar ElSayed | T-09 |
| User guide - Administration, UPD | Omar ElSayed | T-10 |
| Data set in the test database (migrated master data) | Omar ElSayed | All sessions |
| Attendance sheets, quizzes, feedback forms | Omar ElSayed | All sessions |

# 6. Trainer Responsibilities

| Trainer | Role | Sessions |
| --- | --- | --- |
| Ahmed Fahmy | Project Manager & Manufacturing Consultant | T-06 |
| Lobna Zanaty | Accounting Consultant | T-07, T-08 |
| Mayada Salah | Inventory Consultant | T-05 |
| Noha Gamal | Sales, CRM & POS Consultant | T-02, T-03 |
| Omar ElSayed | HR, Purchase & Technical Consultant | T-01, T-04, T-09, T-10 |

# 7. Evaluation

| Method | Description | Target |
| --- | --- | --- |
| Attendance | Signed attendance sheet per session | 90% of invited users attend |
| Hands-on exercise | Each user completes the exercise of their module in the test database | Every user completes it with no blocking error |
| Short quiz | 10 questions per module, open book | 70% correct |
| Feedback form | 5 questions on clarity, pace and usefulness | Average 4 out of 5 |
| Post-go-live check | Hypercare issue log reviewed for training gaps | No repeated 'how do I' issue after 2 weeks |

# 8. After Go-live

- Key users are first-line support for their department during hypercare

- Issues are logged with the System Administrator and escalated to the consultants

- User guides are kept by the System Administrator and updated when a process changes

- New joiners: T-01 plus their module session, delivered by the key user

# 9. Approval

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Dina Samir | HR Manager - Beitak Smart |  |  |
| Omar Hassan | Client Project Manager |  |  |
| Omar ElSayed | HR, Purchase & Technical Consultant - Khomasi ERP |  |  |