Project Documents

Technical Proposal Document (TPD)

Smart Core - Beitak Smart Odoo ERP Implementation

| Client | Beitak Smart |
| --- | --- |
| Implementation partner | Khomasi ERP |
| Project | Smart Core - Beitak Smart Odoo ERP Implementation (BTK-ERP-01) |
| Document ID | BTK-DOC-05 |
| Version | 1.0 |
| Date | 29 Oct 2026 |
| Status | Submitted - for sign-off at M3 (05 Nov 2026) |
| Prepared by | Ahmed Fahmy (Project Manager) |
| Approved by | Hany Mostafa - General Manager (Beitak Smart) |

# Document Control

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0 | 29 Oct 2026 | Ahmed Fahmy | Initial release |

| Distribution | Role |
| --- | --- |
| Hany Mostafa | Project Sponsor - Beitak Smart |
| Omar Hassan | Client Project Manager |
| Khomasi ERP project team | Implementation partner |

# 1. Objective

Khomasi ERP proposes to implement Odoo 19 Enterprise for Beitak Smart so that sales, showroom, purchasing and import, warehouses, assembly, accounting and HR work in one system, with landed-cost-based product cost, real-time stock, serial traceability and profitability by business line and branch.

| Objective | KPI | Target |
| --- | --- | --- |
| Accurate product cost and margin | Import shipments with landed costs allocated | 100% |
| Fewer stock-outs | Stock-out rate on top-20 SKUs | below 3% |
| Reliable stock | Inventory record accuracy at cycle count | 98% or more |
| Faster close | Month-end close duration | 5 working days |
| Receivables control | Days sales outstanding (DSO) | 55 days or less |
| Profitability visibility | P&L by branch and business line | Monthly by working day 5 |
| Sales pipeline | B2B opportunities tracked in CRM | 100% |
| Integrated showroom | POS sales posted to stock and accounting | Automatic, daily |

# 2. Agreed Requirements

The 70 requirements of the BRD (approved at M2) are traced in the RTM. Split: Standard 51 (73%), Workaround 8 (11%), Customization 11 (16%).

| Module | Requirements | Must | Std / Wrk / Cust | Owner |
| --- | --- | --- | --- | --- |
| CRM | 5 | 2 | 4 / 0 / 1 | Noha Gamal |
| Sales | 10 | 5 | 6 / 0 / 4 | Noha Gamal |
| Point of Sale | 5 | 4 | 4 / 1 / 0 | Noha Gamal |
| Purchase | 9 | 5 | 6 / 1 / 2 | Omar ElSayed |
| Inventory | 11 | 7 | 9 / 1 / 1 | Mayada Salah |
| Manufacturing | 8 | 4 | 6 / 2 / 0 | Ahmed Fahmy |
| Accounting | 12 | 11 | 10 / 2 / 0 | Lobna Zanaty |
| Human Resources | 4 | 2 | 4 / 0 / 0 | Omar ElSayed |
| Cross-functional | 6 | 2 | 2 / 1 / 3 | Omar ElSayed |
| Total | 70 | 42 | 51 / 8 / 11 |  |

# 3. Modules and Platform

| App | Scope for Beitak Smart |
| --- | --- |
| CRM | Pipeline by 6 sales teams, activities, lost reasons, targets |
| Sales | 4 price lists, credit control, discount approval, invoicing on delivery, services |
| Point of Sale | Cairo showroom with barcode, serials, cash / card / customer account |
| Purchase | Vendor prices in EGP / USD, PO approval, three-way match, reordering |
| Inventory | 5 warehouses, multi-step routes, resupply, serial numbers, landed costs, counts, scrap |
| Manufacturing | 11 BOMs incl. multi-level fan, 5 work centers, work orders, costing, serials |
| Accounting | Egypt localization, VAT 14%, WHT 1/2/3%, 9 journals, USD, analytic plans, opening balances, reports |
| Employees / Time Off / Attendances | Departments, jobs, employees, leave approval, attendance kiosk |
| Studio | 11 customizations (fields, approval rules, report layouts) |

| Odoo plan | Custom plan - required because Studio is used for the customizations |
| --- | --- |
| Hosting | Odoo Online (SaaS), daily backups; test database duplicated for UAT |
| Integrations | None in phase 1 |
| If a custom module is needed later | Move to Odoo.sh (included in the Custom plan; hosting billed separately) |

# 4. Departments and Employees in Scope

| Department | Employees | Odoo users | Main apps |
| --- | --- | --- | --- |
| General Management | 1 | 1 | All (approvals, dashboards) |
| Finance & Accounting | 4 | 4 | Accounting, POS closing |
| Procurement & Import | 3 | 3 | Purchase, Inventory |
| Sales | 7 | 7 | CRM, Sales |
| Showroom & Retail | 3 | 3 | Point of Sale |
| Warehouse & Logistics | 8 | 6 | Inventory |
| Production | 6 | 2 | Manufacturing, Inventory |
| Quality Control | 1 | 1 | Manufacturing (QC step) |
| Human Resources | 2 | 2 | Employees, Time Off, Attendances |
| IT & ERP | 1 | 1 | Settings, users |
| Total | 36 | 30 |  |

# 5. Users and Privileges

30 users in 19 access profiles. Each user is created from the employee record. Detailed matrix in the UPD.

| Profile | Users | Access rights |
| --- | --- | --- |
| General Manager | 1 | Sales: Administrator, CRM: Administrator, Purchase: Administrator, Inventory: Administrator, Manufacturing: Administrator, Accounting: Auditor (read-only), Point of Sale: Administrator, Employees: Officer |
| Finance Manager | 1 | Sales: User: All Documents, Purchase: User, Inventory: User, Accounting: Administrator, Point of Sale: User |
| Procurement Manager | 1 | Purchase: Administrator, Inventory: User, Accounting: Invoicing / Billing |
| Sales Manager | 1 | Sales: Administrator, CRM: Administrator, Inventory: User, Point of Sale: Administrator |
| Warehouse Manager | 1 | Purchase: User, Inventory: Administrator, Manufacturing: User |
| Production Manager | 1 | Inventory: User, Manufacturing: Administrator |
| HR Manager | 1 | Employees: Administrator |
| System Administrator | 1 | Sales: Administrator, CRM: Administrator, Purchase: Administrator, Inventory: Administrator, Manufacturing: Administrator, Accounting: Administrator, Point of Sale: Administrator, Employees: Administrator, Settings: Administration: Settings |
| Accountant | 2 | Purchase: User, Accounting: Accountant |
| Treasurer / Cashier | 1 | Accounting: Invoicing / Billing, Point of Sale: User |
| Buyer | 2 | Purchase: User, Inventory: User |
| Key Account Manager | 1 | Sales: User: All Documents, CRM: User: All Documents |
| Sales Representative | 5 | Sales: User: Own Documents Only, CRM: User: Own Documents Only |
| Showroom Supervisor | 1 | Sales: User: All Documents, Inventory: User, Point of Sale: Administrator |
| Showroom user | 2 | Point of Sale: User |
| Warehouse Keeper | 5 | Inventory: User |
| Production Supervisor | 1 | Inventory: User, Manufacturing: User |
| QC Inspector | 1 | Inventory: User, Manufacturing: User |
| HR Specialist | 1 | Employees: Officer |

# 6. Execution Plan

| Phase | Activities | Deliverables | Lead |
| --- | --- | --- | --- |
| 1. Initiation & Discovery | Kick-off, workshops per department, company profile, entity data collection | Team & Roles, Company Profile, Scope | Ahmed Fahmy |
| 2. Analysis & Requirements | As-is review, requirements, gap analysis, traceability | BRD, GAWF, RTM | Ahmed Fahmy, Mayada Salah, Noha Gamal |
| 3. Solution Design & Proposals | Module design, customization and workaround design, proposals | SSD, TPD, FPD | All consultants |
| 4. Configuration & Data Migration | Database configuration, 27 import files, 11 customizations, integration tests | Configured test database | All consultants; Omar ElSayed (migration) |
| 5. Testing / UAT | Test scripts per requirement, UAT cycles, defect fixing | UATD signed | Noha Gamal + module owners |
| 6. Training & Change Management | Key-user and end-user training, user guides, communication | TD, UDP | Omar ElSayed + module owners |
| 7. Cutover | Legacy close, stock count, final imports, opening entry, go / no-go | Cutover checklist | Ahmed Fahmy, Lobna Zanaty |
| 8. Go-live & Hypercare | Daily support, issue log, handover to client admin | Hypercare report | All consultants |

# 7. Responsible Team in Both Parties

## 7.1 Khomasi ERP

| Member | Role | Modules |
| --- | --- | --- |
| Ahmed Fahmy | Project Manager & Manufacturing Consultant | Project management, Manufacturing |
| Lobna Zanaty | Accounting Consultant | Accounting, Analytic, Taxes, Opening balances |
| Mayada Salah | Inventory Consultant | Inventory, Landed Costs |
| Noha Gamal | Sales, CRM & POS Consultant | CRM, Sales, Point of Sale |
| Omar ElSayed | HR, Purchase & Technical Consultant | Employees, Purchase, Users & Access, Data Migration |

## 7.2 Beitak Smart

| Name | Job | Project role |
| --- | --- | --- |
| Hany Mostafa | General Manager | Project Sponsor |
| Omar Hassan | IT & ERP Administrator | Client Project Manager & System Administrator |
| Rania Fathy | Finance Manager | Key User - Accounting |
| Sherif Nabil | Procurement & Import Manager | Key User - Purchase & Import |
| Karim Adel | Sales Manager | Key User - Sales & CRM |
| Salma Ashraf | Showroom Supervisor | Key User - Showroom (POS) |
| Tamer Salah | Warehouse & Logistics Manager | Key User - Inventory |
| Mohamed Zaki | Production Manager | Key User - Manufacturing |
| Dina Samir | HR Manager | Key User - HR |

# 8. Time Schedule

13 weeks from 04 Oct 2026 to go-live on 01 Jan 2027, then 4 weeks of hypercare to 28 Jan 2027. Work week Sunday-Thursday.

| Phase / week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | Jan |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Initiation & Discovery | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |
| Analysis & Requirements |  | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |  |
| Solution Design & Proposals |  |  |  | ■ | ■ |  |  |  |  |  |  |  |  |  |
| Configuration & Data Migration |  |  |  |  |  | ■ | ■ | ■ | ■ |  |  |  |  |  |
| Testing / UAT |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |  |
| Training & Change Management |  |  |  |  |  |  |  |  |  |  | ■ | ■ |  |  |
| Cutover |  |  |  |  |  |  |  |  |  |  |  |  | ■ |  |
| Go-live & hypercare |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ |

| Milestone | Date | Evidence |
| --- | --- | --- |
| M1 Project kick-off | 04 Oct 2026 | Kick-off minutes, team & roles |
| M2 BRD sign-off | 22 Oct 2026 | Approved BRD |
| M3 Solution & proposals sign-off | 05 Nov 2026 | Approved SSD, TPD, FPD (RTM baseline) |
| M4 Configuration & data migration complete | 03 Dec 2026 | Configured test database with migrated data |
| M5 UAT sign-off | 17 Dec 2026 | Signed UATD |
| M6 Go-live | 01 Jan 2027 | Production live from fiscal-year start, opening balances posted; first working day Sun 3 Jan 2027 |
| M7 Hypercare closure | 28 Jan 2027 | Hypercare report, handover to client admin |

# 9. Client Responsibilities and Assumptions

- Name key users and give them two days per week during analysis and UAT

- Deliver cleansed master data by the end of week 7 and the final stock count on 30-31 Dec 2026

- Approve deliverables within 3 working days of submission

- Buy the Odoo subscription (Custom plan) before configuration starts (week 6)

- Tax specialist confirms VAT and WHT set-up before UAT

- Scope changes follow the change-request process (priced in the FPD)

## Out of scope

- Payroll (salary calculation) - phase 2 after the Egypt payroll localization is reviewed

- Egyptian e-invoice / e-receipt integration with the Tax Authority - phase 2

- eCommerce website and online payments

- Repairs / field service for warranty visits - phase 2

- Fleet management and vehicle costs

- WhatsApp integration and SMS notifications - phase 2

- Barcode app on handheld scanners - phase 2 (POS barcode scanning is in scope)

- External BI tools (e.g. Power BI) and data warehouse

# 10. Why Khomasi ERP

- A dedicated owner for every module, with accounting and manufacturing know-how in the team

- Data-first approach: entity data and 27 import files prepared before configuration

- Standard-first design: 73% of requirements met with Odoo standard, keeping upgrades simple

- Full traceability from pain point to requirement, design and test case

# 11. Approval

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Hany Mostafa | Project Sponsor - Beitak Smart |  |  |
| Ahmed Fahmy | Project Manager - Khomasi ERP |  |  |