## Index
User Acceptance Test Document (UATD)
Smart Core - Beitak Smart Odoo ERP Implementation ¦ Khomasi ERP ¦ Version 1.0 ¦ 17 Dec 2026
Sheet | Content | Instructor requirement
Test Plan | Two UAT cycles and sign-off | Testing / UAT phase
Acceptance Criteria | Pass rules and defect severity | UAT governance
Test Cases | 25 scenarios covering all requirements | UATD
Results Summary | Automatic pass / fail summary | UAT reporting
Defects | Defect log | UAT
Sign-off | Signatures of key users and sponsor | M5 sign-off
Assumptions
Odoo version | Files target Odoo 18/19 field names (type=Goods + is_storable). On Odoo 17 replace 'type'+'is_storable' with 'detailed_type' = product.
Database | Designed for a NEW clean database with the Egypt fiscal localization. Importing into the old database will clash with existing account codes and products.
Exchange rate | USD/EGP = 50.00 on 2027-01-01. Project assumption, not an official CBE rate.
Landed costs | Cost of imported items = FOB price x 50 x 1.10 (about 10% for freight, duties, clearance and insurance). Assumption.
Sales prices | Sales prices are VAT-exclusive. VAT 14% comes from the Egypt localization default taxes.
Costing | AVCO + automated (perpetual) valuation on all stockable categories. Needed for Landed Costs.
Opening stock | Stock is loaded through Physical Inventory with accounting date 2027-01-01. Its counterpart is account 190100 Opening Stock Clearing, which the opening journal entry closes to zero.
Taxes | VAT 14% and withholding tax 1% / 2% / 3% (team decision). Rates, categories and thresholds must be reviewed by a tax specialist before go-live.
Personal data | All names, emails, phones, tax IDs and bank numbers are fictional placeholders (.example domains).

## Test Plan
UAT Plan
Two cycles in the test database with migrated data. A case passes only when the expected result is met in full.
Stage | Activity | Start | End | Who
UAT 1 | Cycle 1 - execute all test cases | 06 Dec 2026 | 10 Dec 2026 | Key users with consultant support
Fix | Defect fixing and reconfiguration | 13 Dec 2026 | 14 Dec 2026 | Khomasi ERP consultants
UAT 2 | Cycle 2 - retest failed cases and regression | 15 Dec 2026 | 16 Dec 2026 | Key users
Sign-off | Review results and sign the UATD | 17 Dec 2026 | 17 Dec 2026 | Sponsor and key users

## Acceptance Criteria
Acceptance Criteria and Defect Severity
Agreed before UAT starts.
Item | Definition | Consequence
Pass | All Must requirements pass | Go-live can proceed
Conditional pass | All Must pass; some Should / Could open with an agreed date | Go-live proceeds; open items tracked
Fail | Any Must requirement fails | Go-live postponed until retested
Severity 1 | Blocks a core process (cannot invoice, cannot deliver) | Fixed within 1 working day
Severity 2 | Workaround exists | Fixed before go-live
Severity 3 | Cosmetic or reporting detail | Fixed during hypercare

## Test Cases
User Acceptance Test Cases
25 end-to-end scenarios covering all 70 requirements. Module = the module that owns the case; a case often crosses modules (see Requirements). Testers fill the last four columns.
Test ID | Module | Scenario | Tester | Steps | Expected Result | Requirements | Priority | Actual Result | Status (Pass / Fail) | Tested by | Date
TC-01 | CRM | Capture a lead and convert it | Sales Representative | 1. CRM > New lead 'Hurghada Electronics Hub', source Exhibition, team Upper Egypt 2. Schedule a call activity 3. Move to Qualified, then convert to opportunity 4. Log a lost reason on another test lead | Lead appears in the rep's pipeline only; activity shows in the chatter; lost reason recorded in the analysis | BR-CRM-01, BR-CRM-02, BR-CRM-03, BR-CRM-04 | Must
TC-02 | Sales | Quotation with wholesale price list | Sales Representative | 1. New quotation for El Nour Electronics 2. Add 12 x LG Smart TV 50 Inch 3. Check unit price against the Wholesale price list (7% off from 10 units) | Price applied automatically from the price list; margin visible to the manager | BR-SAL-01, BR-SAL-02, BR-SAL-09 | Must
TC-03 | Sales | Credit limit warning and approval | Sales Rep + Finance Manager | 1. Create an order for a customer whose exposure exceeds the credit limit 2. Try to confirm 3. Finance Manager approves | Warning shown on the order; confirmation blocked until the Finance Manager approves | BR-SAL-03, BR-SAL-04 | Must
TC-04 | Sales | Discount above 10% | Sales Rep + Sales Manager | 1. Set a 15% line discount 2. Try to confirm the order 3. Sales Manager approves | Confirmation requires Sales Manager approval; approval logged in the chatter | BR-SAL-05 | Should
TC-05 | Sales | Deliver and invoice | Warehouse Keeper + Accountant | 1. Confirm the order 2. Pick, pack and ship with serial scanning 3. Create the invoice 4. Open the journal items | Invoice shows delivered quantities only; entries: AR / revenue + VAT, and COGS / stock output; bilingual layout prints correctly | BR-SAL-06, BR-SAL-08, BR-INV-06, BR-ACC-12 | Must
TC-06 | Accounting | Customer payment and cheque | Treasurer + Accountant | 1. Register a bank payment for one invoice 2. Register a post-dated cheque for another (110300) 3. Reconcile the bank statement 4. Open the Aged Receivable report | Invoices reconciled; cheque sits in notes receivable until collection; aged report matches the customer balance; each bank and cash journal reconciles to its account | BR-ACC-05, BR-ACC-06, BR-ACC-04 | Must
TC-07 | POS | Showroom sale through POS | Showroom Cashier + Supervisor | 1. Open the session with the opening cash count 2. Scan an appliance barcode and select its serial 3. Pay half cash, half card 4. Supervisor refunds a test order 5. Close the session with a cash count | Serial recorded on the order; stock reduced in CAW; cashier cannot refund; closing entry posts to cash, bank and sales; difference to 999001 / 999002 | BR-POS-01, BR-POS-02, BR-POS-03, BR-POS-04, BR-POS-05 | Must
TC-08 | Purchase | Purchase order and approval | Buyer + Procurement Manager | 1. Create a local PO above 250,000 EGP 2. Try to confirm as buyer 3. Procurement Manager approves | PO goes to 'To Approve'; only the manager can confirm | BR-PUR-01, BR-PUR-02 | Must
TC-09 | Purchase | Import shipment with landed costs | Import Specialist + Accountant | 1. PO in USD to Guangzhou Coolair with container and ETA fields 2. GM confirms 3. Receive through Input > QC > Stock 4. Post bills for freight, duties, clearance and insurance 5. Create and validate the landed cost on the receipt 6. Check the product cost and the shipment cost sheet | Product cost increases by the allocated landed costs; clearing accounts 1301xx net to zero; cost sheet shows cost per unit | BR-PUR-03, BR-PUR-05, BR-PUR-06, BR-PUR-09, BR-INV-03 | Must
TC-10 | Purchase | Vendor bill three-way match and USD payment | Accountant + Treasurer | 1. Create the vendor bill from the PO 2. Change a quantity to differ from the receipt 3. Correct it and post 4. Pay from the CIB USD account at a different rate 5. Open the purchase analysis by vendor, product and currency | Bill control flags the mismatch; payment posts the exchange difference to 500011 / 400053; purchase analysis shows both currencies | BR-PUR-04, BR-ACC-03, BR-PUR-07 | Must
TC-11 | Accounting | Withholding tax on a local bill | Accountant | 1. Post a bill for a service vendor with WHT 2. Check the tax lines and the payable amount | WHT reduces the payable and credits 201020; amounts match the agreed rate | BR-ACC-02 | Must
TC-12 | Inventory | Automatic replenishment | Warehouse Manager | 1. Bring a product below its minimum 2. Run Replenishment 3. Check the created RFQ and the created MO for a manufactured item | RFQ created for Buy products and MO for Manufacture products, up to the maximum quantity | BR-INV-02, BR-PUR-08, BR-MRP-04 | Must
TC-13 | Inventory | Branch resupply transfer | Warehouse Keeper | 1. Transfer 10 units from Cairo to Alexandria 2. Validate both the outgoing and incoming steps | Stock moves between warehouses; both warehouse quantities update; no accounting impact | BR-INV-05, BR-INV-01 | Must
TC-14 | Manufacturing | Fan manufacturing (multi-level) | Production Supervisor + QC Inspector | 1. Create an MO for 10 Beitak Stand Fans 2. Produce the control board sub-assembly first 3. Run the work orders with timers 4. Scrap one component 5. QC finishes the last operation 6. Produce with generated serials | Components consumed from the raw-material store; WIP cleared; finished goods valued at components + labour; 10 serials created; scrap posted to 400036 | BR-MRP-01, BR-MRP-02, BR-MRP-03, BR-MRP-05, BR-MRP-06, BR-MRP-07 | Must
TC-15 | Inventory | Serial traceability and warranty | Warehouse Keeper + Sales Rep | 1. Open a delivered serial 2. Check its traceability report 3. Check the warranty end date 4. Return the unit to quality control | Full movement history shown; warranty date computed from the delivery date; return received into QC | BR-INV-06, BR-INV-07, BR-INV-11 | Must
TC-16 | Inventory | Cycle count | Warehouse Keeper + Warehouse Manager | 1. Keeper counts one location and enters quantities 2. Keeper tries to apply 3. Manager applies | Only the manager can apply; adjustment entry posted to the inventory accounts | BR-INV-09, BR-INV-08 | Must
TC-17 | Accounting | Month-end close and reports | Finance Manager + Senior Accountant | 1. Reconcile banks and cash 2. Compare stock valuation with GL 1201xx 3. Run trial balance, P&L, balance sheet and VAT report 4. Run the P&L by branch and by business line 5. Set the lock date | Stock valuation equals the GL; reports balance; analytic reports show both plans; entries before the lock date are blocked | BR-ACC-07, BR-ACC-09, BR-ACC-11, BR-ACC-12 | Must
TC-18 | Accounting | Opening balances | Finance Manager | 1. Open the opening journal entry 2. Check account 190100 3. Compare partner balances with the legacy aging | Trial balance balanced at 1 Jan 2027; 190100 equals zero; partner balances match the legacy system | BR-ACC-10, BR-ACC-01, BR-GEN-01 | Must
TC-19 | Accounting | Payment approval and dashboard | Treasurer + Finance Manager | 1. Treasurer drafts a payment above 500,000 EGP 2. Finance Manager posts it 3. Open the management dashboard | Treasurer cannot post; dashboard shows sales, stock value and overdue receivables | BR-ACC-08, BR-GEN-04 | Should
TC-20 | HR | HR: employee, leave and attendance | HR Specialist + Manager + Employee | 1. Create an employee with department and manager 2. Employee requests annual leave 3. Manager approves 4. Check in and out on the attendance kiosk | Employee visible in the org chart; leave approved by the direct manager only; attendance recorded | BR-HR-01, BR-HR-02, BR-HR-03 | Must
TC-21 | Cross-functional | Access rights and audit trail | System Administrator | 1. Log in as a sales rep and try to open another rep's opportunity 2. Log in as a warehouse keeper and try to open accounting 3. Change a product sales price and open the chatter 4. Print a delivery slip and the driver trip sheet | Rep sees only own documents; keeper has no accounting menu; price change tracked in the chatter; documents print bilingual with serials and driver | BR-HR-04, BR-GEN-02, BR-GEN-03, BR-GEN-05, BR-GEN-06 | Must
TC-22 | CRM | Salesperson target and commission | Sales Manager | 1. Set a monthly target for a rep 2. Open the achievement report 3. Open the commission report after collection | Achievement % calculated against invoiced revenue; commission based on collected invoices only | BR-CRM-05, BR-SAL-10 | Should
TC-23 | Sales | Installation service on an order | Sales Representative | 1. Add an AC and an installation service on one order 2. Invoice | Service invoiced on ordered quantity; revenue posted to 510500 | BR-SAL-07 | Should
TC-24 | Manufacturing | Scrap review and production analysis | Production Manager | 1. Open the weekly scrap report filtered above 10,000 EGP 2. Compare planned and real work-order duration 3. Compare MO cost with the BOM cost | Scrap list available for review and sign-off; variances visible | BR-INV-10, BR-MRP-08 | Should
TC-25 | Inventory | Warehouse delivery steps | Warehouse Keeper | 1. Deliver from Cairo (pick, pack, ship) 2. Deliver from Alexandria (pick, ship) | Each warehouse follows its configured steps | BR-INV-04 | Should

## Results Summary
UAT Results Summary
Updates automatically from the Status column of the Test Cases sheet.
Module | Test cases | Passed | Failed | Not tested | Pass %
CRM | 2 | 0 | 0 | 2 | 0%
Sales | 5 | 0 | 0 | 5 | 0%
POS | 1 | 0 | 0 | 1 | 0%
Purchase | 3 | 0 | 0 | 3 | 0%
Inventory | 5 | 0 | 0 | 5 | 0%
Manufacturing | 2 | 0 | 0 | 2 | 0%
Accounting | 5 | 0 | 0 | 5 | 0%
HR | 1 | 0 | 0 | 1 | 0%
Cross-functional | 1 | 0 | 0 | 1 | 0%
Total | 25 | 0 | 0 | 25 | 0%
Go-live readiness
All Must test cases passed? | Not yet
Open defects (Severity 1 or 2) | 0

## Defects
Defect Log
One row per defect found during UAT. Severity per the Acceptance Criteria sheet.
Defect ID | Test ID | Description | Severity (1-3) | Status | Raised by | Assigned to | Date raised | Date fixed | Retest result
DEF-001 |  | (example - delete before use) | 3 | Closed

## Sign-off
UAT Sign-off
Signed at milestone M5 on 17 Dec 2026. Signing confirms the tested scope works as designed.
Name | Role | Area tested | Signature | Date
Hany Mostafa | Project Sponsor | Overall acceptance
Rania Fathy | Key User - Accounting | Accounting, opening balances
Karim Adel | Key User - Sales & CRM | Sales, CRM
Salma Ashraf | Key User - Showroom | Point of Sale
Sherif Nabil | Key User - Purchase | Purchase, import, landed costs
Tamer Salah | Key User - Inventory | Warehouses, serials, counts
Mohamed Zaki | Key User - Manufacturing | BOMs, work orders, costing
Dina Samir | Key User - HR | Employees, time off
Noha Gamal | Sales, CRM & POS Consultant - Khomasi ERP | UAT coordination
Ahmed Fahmy | Project Manager - Khomasi ERP | Project