Entity Data & Implementation Setup

Go-Live and Deployment Plan

Smart Core - Beitak Smart Odoo ERP Implementation

| Client | Beitak Smart |
| --- | --- |
| Implementation partner | Khomasi ERP |
| Project | Smart Core - Beitak Smart Odoo ERP Implementation (BTK-ERP-01) |
| Document ID | BTK-IMP-01 |
| Version | 1.0 |
| Date | 24 Dec 2026 |
| Status | Approved |
| Prepared by | Ahmed Fahmy (Project Manager) |
| Approved by | Hany Mostafa - General Manager (Beitak Smart) |

# Document Control

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0 | 24 Dec 2026 | Ahmed Fahmy | Initial release |

| Distribution | Role |
| --- | --- |
| Hany Mostafa | Project Sponsor - Beitak Smart |
| Omar Hassan | Client Project Manager |
| Khomasi ERP project team | Implementation partner |

# 1. Purpose and Go-live Strategy

This plan covers the move from the legacy systems to Odoo production. The approach is a big-bang go-live on 01 Jan 2027: all modules and all locations start together at the beginning of the fiscal year, so no opening balances have to be split across periods.

| Go-live date | 01 Jan 2027 (Friday - first working day Sunday 3 Jan 2027) |
| --- | --- |
| Opening balance date | 01 Jan 2027 |
| Cutover window | 28 Dec 2026 to 01 Jan 2027 |
| Stock count | 30-31 December 2026, all 5 warehouses and the showroom |
| Legacy systems | Closed for posting on 31 Dec 2026; kept read-only for history |
| Hypercare | 01 Jan 2027 to 28 Jan 2027 |
| Decision | Go / no-go meeting on 01 Jan 2027, chaired by the sponsor |

# 2. Preparation (before cutover)

| ID | Activity | Owner | When | Evidence |
| --- | --- | --- | --- | --- |
| P-01 | Production database created from the signed test database; configuration compared field by field | Omar ElSayed | Week 12 | Configuration checklist signed |
| P-02 | Odoo subscription (Custom plan) active with 30 users | Omar Hassan | Week 12 | Subscription confirmation |
| P-03 | Users created from employee records with the UPD access profiles; invitation emails sent | Omar ElSayed | Week 12 | User list exported and signed |
| P-04 | All master-data import files frozen (no further changes without a change request) | Omar ElSayed | Week 12 | Files tagged v-final in the repository |
| P-05 | Training completed; attendance and quiz results collected | Omar ElSayed | Week 13 | Training report |
| P-06 | Serial-number labels printed and attached to every appliance in all 5 warehouses | Tamer Salah | Week 12-13 | Labelling confirmed per warehouse |
| P-07 | Cut-off memo issued to all departments (no backdated documents in the legacy system after 31 Dec) | Rania Fathy | Week 12 | Memo circulated |
| P-08 | USD rate for 1 Jan 2027 agreed with the Finance Manager (CBE rate) | Lobna Zanaty | 27 Dec 2026 | Rate recorded in the cutover log |
| P-09 | Backup of the legacy system taken and archived read-only | Omar Hassan | 31 Dec 2026 | Backup confirmation |

# 3. Cutover Plan

| # | Date | Activity | Executed by | Verified by |
| --- | --- | --- | --- | --- |
| 1 | 28 Dec 2026 (Mon) | Freeze master data: last changes to customers, vendors, products and BOMs in the legacy files | Key users | Omar ElSayed |
| 2 | 28 Dec 2026 (Mon) | Import files 01-23 into production (accounts, journals, analytic, HR, partners, products, BOMs, warehouses, locations, serials) | Omar ElSayed | Lobna Zanaty |
| 3 | 29 Dec 2026 (Tue) | Verify imported masters: counts per file, spot checks by each key user | Key users | Omar Hassan |
| 4 | 29 Dec 2026 (Tue) | Set valuation accounts on virtual locations (190100, 120850, 400036) | Omar ElSayed | Lobna Zanaty |
| 5 | 30-31 Dec 2026 | Full physical stock count in all 5 warehouses and the showroom; warehouses closed for movements | Warehouse keepers | Tamer Salah |
| 6 | 31 Dec 2026 (Thu) | Legacy system closed: last invoices, bills, payments posted; trial balance at 31 Dec 2026 extracted | Rania Fathy | Lobna Zanaty |
| 7 | 31 Dec 2026 | Counted quantities entered in file 24 and imported; Physical Inventory applied with accounting date 1 Jan 2027 | Omar ElSayed | Tamer Salah |
| 8 | 31 Dec 2026 | Partner balances (AR, AP, cheques) confirmed against the legacy aging reports | Nourhan Ibrahim | Rania Fathy |
| 9 | 01 Jan 2027 (Fri) | USD rate entered; opening journal entry (file 27) imported and posted | Lobna Zanaty | Rania Fathy |
| 10 | 01 Jan 2027 (Fri) | Validation pack run (section 4); reordering rules and open opportunities imported (files 25-26) | Omar ElSayed | Ahmed Fahmy |
| 11 | 01 Jan 2027 (Fri) | Open documents loaded: unshipped sales orders, open purchase orders, open manufacturing orders | Key users | Ahmed Fahmy |
| 12 | 01 Jan 2027 (Fri) | Go / no-go meeting | Ahmed Fahmy | Hany Mostafa |
| 13 | 02 Jan 2027 (Sat) | Production backup taken; users unlocked; login test by one user per department | Omar Hassan | Omar ElSayed |
| 14 | 3 Jan 2027 (Sun) | First working day: POS session opened, first delivery and first invoice issued with a consultant watching | All departments | Ahmed Fahmy |

Each step is signed off in the cutover log before the next one starts. Nothing is posted in production before step 12.

# 4. Data Validation Pack

| ID | Check | Expected result | Owner |
| --- | --- | --- | --- |
| V-01 | Trial balance at 1 Jan 2027 is balanced | Debit = Credit = 40,474,776.50 EGP | Lobna Zanaty |
| V-02 | Opening Stock Clearing 190100 is zero | Balance = 0.00 | Lobna Zanaty |
| V-03 | Stock valuation report equals the GL inventory accounts | Total = 20,424,776.50 EGP across 1201xx / 120800 | Rania Fathy |
| V-04 | Customer balances match the legacy aging | AR 3,750,000.00 + cheques 580,000.00 EGP by partner | Nourhan Ibrahim |
| V-05 | Vendor balances match the legacy aging | AP 4,800,000.00 + cheques 720,000.00 EGP by partner | Nourhan Ibrahim |
| V-06 | Serial numbers loaded equal the physical count | 1,546 serials, one per appliance unit | Tamer Salah |
| V-07 | Stock quantities per warehouse match the count sheets | Per warehouse and per location | Warehouse keepers |
| V-08 | Product costs loaded and no product has zero cost | 89 products with cost | Lobna Zanaty |
| V-09 | BOM cost roll-up equals the loaded product cost | 11 BOMs, difference 0.00 | Ahmed Fahmy |
| V-10 | Bank and cash opening balances match the statements and counts | 8 journals | Wael Said |
| V-11 | All 30 users can log in with the correct menus | One test per access profile | Omar Hassan |
| V-12 | Taxes apply correctly on a test invoice and a test bill | VAT 14%, WHT as configured | Mahmoud Ali |
| V-13 | POS session opens and closes with correct entries | Test session in production, then reversed | Salma Ashraf |
| V-14 | Customizations work in production (11 items) | CU-01 to CU-11 spot-checked | Omar ElSayed |

# 5. Go / No-Go Criteria

| Criterion | Type |
| --- | --- |
| All validation checks V-01 to V-14 passed | Mandatory |
| All Must UAT test cases passed (UATD) | Mandatory |
| No open severity-1 defect | Mandatory |
| Training completed for at least 90% of users | Mandatory |
| Subscription active and users able to log in | Mandatory |
| Key users available for the first working week | Mandatory |
| Open severity-2 defects have an agreed fix date | Recommended |
| Rollback option tested (section 6) | Recommended |

Attendees: sponsor, client project manager, all key users, partner project manager. A no-go moves the go-live to the next month-end and the opening date changes to 1 Feb 2027.

# 6. Rollback Plan

| Situation | Safety net | Rollback action | Decision by |
| --- | --- | --- | --- |
| Before any import | Manual backup of the production database | Restore the backup and repeat the step | Omar ElSayed |
| Wrong master-data import | External IDs used in every file | Re-import the corrected file; records update instead of duplicating | Omar ElSayed |
| Wrong opening stock | Physical Inventory applied in one batch | Reverse the inventory adjustment entry and re-apply the corrected count | Tamer Salah |
| Wrong opening entry | Single journal entry OPENING-2027 | Reset to draft, correct and post again (before any transaction is posted) | Lobna Zanaty |
| Major failure after go-live | Legacy system kept read-only and the last backup available | Sponsor decides: continue in Odoo with fixes, or work on paper for up to 2 days while the issue is fixed | Hany Mostafa |

# 7. Hypercare

| Period | Support | Who |
| --- | --- | --- |
| Week 1 (3-7 Jan) | One consultant on site daily; daily 15-minute stand-up with key users | Consultants + key users |
| Week 2 (10-14 Jan) | On site for the first stock transfers and the first vendor payments; remote otherwise | Consultants |
| Week 3 (17-21 Jan) | Remote support; support for the first VAT review | Consultants |
| Week 4 (24-28 Jan) | First month-end close in Odoo supported end to end; handover meeting | Lobna Zanaty + Ahmed Fahmy |

## 7.1 Support Escalation

| Level | Raised by | Handled by | Response time |
| --- | --- | --- | --- |
| 1 | End user | Key user of the department | Same day |
| 2 | Key user | System Administrator (Omar Hassan) | Same day |
| 3 | System Administrator | Khomasi ERP module consultant | Severity 1: same day; 2: 2 working days; 3: during hypercare |
| 4 | Module consultant | Project Manager (Ahmed Fahmy) then the sponsor | Blocking issues only |

# 8. Cutover Risks

| Risk | Level | Mitigation |
| --- | --- | --- |
| Count differences between the count sheets and the legacy stock | High | Count 30-31 Dec with warehouses closed; differences investigated before import; Finance Manager approves the final figures |
| Legacy balances change after extraction | Medium | Cut-off memo; legacy closed for posting on 31 Dec |
| Users cannot log in on the first day | Medium | Login test for every profile on 2 Jan; administrator available |
| Backlog of documents during the freeze | Medium | Freeze is 4 days including a weekend; urgent deliveries recorded on paper and entered on 3 Jan |
| Exchange-rate dispute on opening USD balances | Low | CBE rate of 31 Dec agreed in writing and recorded in the cutover log |
| Key user absent during cutover | Medium | Named backup for each key user in the cutover log |

# 9. Post Go-live Review

| When | Review | Owner |
| --- | --- | --- |
| End of week 1 | First deliveries, invoices and POS sessions posted correctly | Ahmed Fahmy |
| End of week 2 | Bank reconciliation done for the first two weeks | Lobna Zanaty |
| End of week 4 | January close completed in 5 working days; hypercare report issued | Lobna Zanaty |
| Month 3 | KPI review against the BRD targets (stock-outs, DSO, close duration) | Ahmed Fahmy + Rania Fathy |
| Month 6 | Full KPI review and phase-2 scoping (payroll, e-invoice, repairs) | Hany Mostafa |

# 10. Handover

- System administration handed to Omar Hassan (IT & ERP Administrator) at the end of hypercare

- Documentation handed over: all project documents, entity data workbooks, 27 import files, user guides

- Open items transferred to a support log with agreed dates

- Optional monthly support contract starts after hypercare (see the FPD)

# 11. Approval

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Hany Mostafa | Project Sponsor - Beitak Smart |  |  |
| Rania Fathy | Finance Manager - Beitak Smart |  |  |
| Tamer Salah | Warehouse & Logistics Manager - Beitak Smart |  |  |
| Omar Hassan | Client Project Manager / System Administrator |  |  |
| Ahmed Fahmy | Project Manager - Khomasi ERP |  |  |